## Issues
Phase 7 issue log (severity per the acceptance criteria)
id | severity | category | status | title | evidence | root_cause | correction | regression | impact
ISS-01 | Medium | Reproducibility / documentation | Corrected (documentation) and regression-tested | Documented command to regenerate the cleaned CSV writes it to the wrong folder | HOW_TO_RUN step 0 said 'python src\clean_fpa_monthly_close.py'. Without --output-dir the script writes to <Downloads>\fpa_monthly_close_cleaned\ (src/clean_fpa_monthly_close.py resolve_output_dir), but the pipeline reads data\processed\ (src/phase4_pipeline.py DEFAULT_CSV). | The cleaner's default output folder was designed for the stand-alone Phase 2 run; the repository instructions did not add the folder argument. | HOW_TO_RUN.txt step 0 now reads 'python src\clean_fpa_monthly_close.py --output-dir data\processed'. Original kept in evidence/originals_before_correction/. | Fresh copy without cleaned CSV and DB: corrected command -> SHA-256 c184b677... in data/processed, pipeline exit 0, tests pass (checks RG.*). | Another analyst following the instructions would get 'missing input' from the pipeline. No financial figure affected.
ISS-02 | Medium | Reproducibility / test design | Corrected (documentation); code unchanged | Following the documented order after a database rebuild produces 2 failing Phase 5 tests | Isolated re-run: step 2 rebuilt phase4_fpa.duckdb (SHA-256 changed although all 72 output CSVs and both documents are byte-identical); step 4 'pytest tests' then gave 123 PASS / 2 FAIL (Phase 5 tests compare the DB hash recorded in the workbook). After step 5 regenerated the workbook the Phase 5 tests passed. | A DuckDB database file is not byte-reproducible between builds; the workbook manifest uses the file hash as the database identity. | HOW_TO_RUN step 4 now says to run 'pytest tests --ignore=tests\test_phase5_excel.py' after a rebuild and to run the Phase 5 tests in step 5. Longer-term (not applied): fingerprint the DB by its output-table hashes instead of the file hash. | Corrected sequence in a fresh copy: all steps exit 0 (checks RG.*). | False test failures; no figure affected.
ISS-03 | Low | Privacy / publication readiness | Open - action before publication | QC files record build-machine paths | data/processed/QC_Report.txt and qc_summary.json contain /mnt/user-data/uploads/... and /tmp/claude-0/.../scratchpad/... paths. .gitignore excludes data/processed/*.csv only, so these two files would be committed. | The cleaner writes absolute input/output paths into its reports. | Before publishing: regenerate from the repository with relative paths or redact the path lines. Not applied in Phase 7 (would change approved Phase 2 outputs; no accuracy impact). | n/a | Machine-specific information only; no credentials or personal data found.
ISS-04 | Low | Reproducibility | Open (accepted) | Phase 6 QA suite finds the palette validator through a machine-specific path | tests/phase6_dashboard_qa.py globs /tmp/claude-0/bundled-skills/...; on another machine that one check is reported as SKIP. | External helper script not vendored into the repository. | Vendor the validator or document the SKIP. Not applied. | n/a | One colour-palette check not reproducible elsewhere.
ISS-05 | Low | Reproducibility | Open - NOT TESTED | No clean-machine install was performed; installed numpy differs from the pin | requirements.txt pins numpy==2.4.6; the QA container has numpy 2.5.3 (other pins match). All re-runs used the existing environment. Nothing has been run on Windows. | Environment constraint. | Run 'python -m venv .venv; pip install -r requirements.txt; pip check' and the HOW_TO_RUN steps on the Windows laptop. | n/a | Unknown until run.
ISS-06 | Accepted limitation (publication blocker) | Provenance / licence | BLOCKED - owner decision | Synthetic status, provenance and redistribution rights of the dataset are unverified | docs/DATA_PROVENANCE.md; the raw CSV has been tracked by git since Stage 0 (commit 1d601c0) and the repository has a GitHub remote; the dashboard embeds 136,330 journal lines (58,340 with document numbers). Repository visibility was not checked in Phase 7. | No licence or source document exists. | Owner to document origin/licence, confirm the GitHub repository is private, and decide whether raw data, cleaned data, workbook and dashboard may be redistributed. | n/a | Publication must wait.
ISS-07 | Accepted limitation | Population rule | Disclosed | Posted-only rule (R6) is provisional; only 58,340 of 152,682 rows (38.2%) are reported | Independent re-derivation matches row-by-row (L47); 82,986 rows excluded by status; status mix is uniform across entities (possible generated noise). Status scenarios move revenue from $202.6M (Posted) to $471.6M (all statuses). | Owner decision pending | Owner to confirm treatment of Pending/Parked/blank. | n/a | Headline totals depend on this rule; disclosed everywhere (AS01).
ISS-08 | Accepted limitation | Scale restoration | Disclosed | Scale restoration (6,265 rows: 1,814 HIGH, 4,451 MEDIUM) is provisional; 73 rows undetermined | Counts verified (L32-L35); in the Posted population 2,374 restored rows. Result proxy: adjusted $26.32M vs as-reported $25.51M vs HIGH-only $29.44M (F_I1). | report_scale labels unreliable | Owner to confirm the rule. | n/a | Disclosed; dashboard scale selector shows the range.
ISS-09 | Accepted limitation | Sign convention | Disclosed | Account sign convention (R9) unresolved; no favourable/unfavourable labels | AS02; GL 4190 discounts negative on 58% of lines. | Data | Owner decision | n/a | Variances are shown as actual - budget only.
ISS-10 | Accepted limitation | FX | Disclosed | 2,517 zero FX rates and missing rates unresolved; USD columns used as reported | D08/D08b, AS05; no metric converts local currency. | Data | Owner decision | n/a | None on reported USD figures.
ISS-11 | Accepted limitation | Duplicates | Disclosed | 3,930 duplicate-candidate rows (incl. 1,587 sign-conflict) retained, none deleted | D06/D07; exclusion scenarios in F_I1. | No confirmed duplicate rule | Owner decision | n/a | Up to $1.6M revenue sensitivity, disclosed.
ISS-12 | Accepted limitation | Forecast | Disclosed | Forecast has no version / as-of date: no forecast-skill claim | AS06 | Data | n/a | n/a | WAPE/bias shown descriptively only.
ISS-13 | Accepted limitation | Gross profit | Disclosed | Gross-profit discount treatment unresolved: S1, S2, S3 kept separate | F_E1, F_E2 (three distinct values), X35-X36 | Data | n/a | n/a | Disclosed as a range.
ISS-14 | Accepted limitation | Balance sheet / KPIs | Disclosed | Balance-sheet basis not established; DSO, DPO, working capital, close duration not computed | AS08-AS10; outputs/phase4/h6_bs_metrics_not_computed.csv | Data | n/a | n/a | None (correctly not computed).
ISS-15 | Accepted limitation | Units | Disclosed | NOS vs EA unit equivalence unverified; no unit economics built | AS11, AS20 | Data | n/a | n/a | None.
ISS-16 | Accepted limitation | Parsing | Evidence supports current reading | About 9,100-9,300 amounts per column look like 'n,nnn' (thousands or 3-decimal comma) | L22, L23: 7,563 testable actuals; 6,940 fit the thousands reading via local/FX within 2% or 1 USD, 0 fit the decimal reading. | Mixed source formats | None needed | n/a | Low residual risk.
ISS-17 | Low | File inventory | Open - housekeeping | A different file with the raw file's name exists in the owner's Downloads folder | Downloads\fpa_monthly_close_raw_messy.csv: 51,675,512 bytes, SHA-256 845b78d8..., same 152,682 rows but different formatting/whitespace (149,469 rows differ). The approved raw is 51,938,535 bytes, a0e6edde.... The cleaner searches the Downloads folder by default; its integrity gate refuses the wrong file. | An earlier copy (probably re-saved by another tool). | Rename or archive the Downloads copy so it cannot be mistaken for the source. | n/a | None while the integrity gate is kept on.
ISS-18 | Low | Documentation / dashboard scope | Open - documentation | 4,996 status-excluded lines are in no dashboard view | Non-Posted lines that also have no actual amount (4,958) or an undetermined scale (38) fail the documented any-status gates, so neither payload contains them (waterfall W32-W33). They are counted in the Phase 4 waterfall and the workbook's Data Quality sheet. | Intended by the documented population definition; not stated on the dashboard's status view. | Add one sentence to the dashboard status note / README in the documentation phase. Not applied (no redesign in Phase 7). | n/a | A reader could assume the status diagnostic covers all 82,986 status exclusions.

## Not_passed_checks
Every check that did not PASS (FAIL / BLOCKED / NOT TESTED)
id | area | check | population | definition | expected | actual | abs_diff | rel_diff | tolerance | status | explanation / evidence note | evidence
UI50 | Phase 6 dashboard (browser) | Firefox / Safari (WebKit) rendering | [7 empty] | NOT TESTED | only Chromium is installed in this environment
UI51 | Phase 6 dashboard (browser) | Screen reader / assistive technology | [7 empty] | NOT TESTED | no assistive technology available; ARIA attributes are not a substitute
UI52 | Phase 6 dashboard (browser) | Physical printer output | [7 empty] | NOT TESTED | print-media emulation and Chromium PDF only
PR.03.detail | Python/SQL/Excel re-runs & reproducibility | Documented step 4 (pytest tests) right after a DB rebuild, ORIGINAL instructions (before the ISS-02 correction): PASS/FAIL/SKIP |  |  | 0 FAIL | 123 PASS / 2 FAIL / 0 SKIP |  |  |  | FAIL | FAILED: test_lineage_and_source_identity_recorded, test_manifest_matches_the_saved_workbook_and_inputs - DB SHA-256 changed on rebuild (ISS-02)
ENV.clean_machine | Python/SQL/Excel re-runs & reproducibility | Clean-machine reproduction (fresh OS + pip install -r requirements.txt) | [7 empty] | NOT TESTED | Re-runs used this container's existing Python 3.13.16 / pandas 3.0.5 / numpy 2.5.3 (pinned 2.4.6) / duckdb 2.0.0 / openpyxl 3.1.5 / pytest 9.2.0; no venv install, no Windows run
SEC.prov | Security, privacy & publication | Data provenance and redistribution licence | [7 empty] | BLOCKED | Owner states the data is synthetic; no licence or provenance document exists to verify it (docs/DATA_PROVENANCE.md). Cannot be resolved by testing.